## Feature List
Feature | Benefit(s)
Website Login | Offers secure system login for the bank employees
Manage Customer Information | Facility for bank employees to quickly onboard a new customer, update customer details & closures
Manage Account details | A convenient and safe experience for opening a new bank account, maintaining the account & closures
Online search | Facility for bank employees to carry out online search on cuastomers and accounts
Operate Banking transactions | Facility for bank employees to carry out customer transactiuons

## Product Backlog
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initiial Size Estimate (SP) | Business Priority | Sprint Number | Comments
Website Login | US001 | As a customer-account executive /cashier / teller I want to be able to log in the bank website with my user ID and password So that I carry out my transactions | * The log in page should be user id and password protected * The user ID can be alphabetic or alphanumeric and should have a minimum of 8 characters * Password should contain 10 characters including one special character, one upper case, one numeric. *Session Management should be done on Login and Logout. Note : Ref Fig1 – Screens_RetailBank_Casestudy.doc | 10 | 1 | 1 | Login page is critical for any bank application.
Manage Customer Information | US002 | As a customer-account executive I want to be able to capture new customer information So that I can create a new customer in the system | * Should be able to enter the values on the screen * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig2 – Screens_RetailBank_Casestudy.doc | 6 | 2 | 1 | For any bank system customer is important So, priority is high.
| US003 | As a customer-account executive I want to be able to edit existing customer information So that I can store the updated customer information in the system | * Should be able to view the details before updating (US009) * Updates of Key customer info like SSN should not be permitted * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig3 – Screens_RetailBank_Casestudy.doc | 8 | 2 | 1 | System should be able to update customer information.
| US004 | As a customer-account executive I want to be able to delete existing customer from system | * Should be able to view the details before deleting (US009) * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig4 – Screens_RetailBank_Casestudy.doc | 13 | 3 | 1 | Delete functionality is also important
| US005 | As a customer-account executive I want to be able to view the status of all the customers of the bank | * Should be able to view the status of all the customers of the bank * Should display only finite number of records per screen * Should be able to refresh and get the latest status of each customer Note : Ref Fig5 – Screens_RetailBank_Casestudy.doc | 16 | 4 | 1 | It is less important task than other task.but it is relatively difficult.
Manage Account Details | US006 | As a customer-account executive I want to be able to capture account details So that I can create a new bank account for an existing customer | * Should be able to create account for existing customer only * Should be able to create different types of accounts * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig6 – Screens_RetailBank_Casestudy.doc | 6 | 2 | 1 | For any transaction to happen account must be created.
| US007 | As a customer-account executive I want to be able to delete an account of an existing customer | * Should be able to view the account details before deleting (US010) * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig7 – Screens_RetailBank_Casestudy.doc | 8 | 3 | 1 | Delete utility of the records should always be given. The accounts records should always be flexible enogh to change their staus according to the deletion proccess.
| US008 | As a customer-account executive I want to be able to view the status of all the accounts of the bank | * Should be able to view the status of all the accounts maintained in the bank * Should display only finite number of records per screen * Should be able to refresh and get the latest status of each account Note : Ref Fig8 – Screens_RetailBank_Casestudy.doc | 16 | 4 | 1 | Live status showing of the account details is the hardest part of the developing.
Online Search | US009 | As a customer-account executive I want to be able to search for a customer So that I am able to view the details | * Should be able to search for the customer details using SSN ID or Customer Id * User friendly responses should be provided for both success & failure Note : Ref Fig9 – Screens_RetailBank_Casestudy.doc | 1 | 1 | 1 | Searching Customer details from the data is the easy part in the software developing.
| US010 | As a Cashier/ Teller I want to be able to search for a bank account So that I am able to view the details | * Should be able to search for the account details using Account ID or Customer Id * User friendly responses should be provided for both success & failure Note : Ref Fig10 – Screens_RetailBank_Casestudy.doc | 2 | 1 | 1 | Searching Account related information should be provided but it is also a easy part to execute.
Operate Banking Transactions | US011 | As a Cashier/ Teller I want to be able to deposit money into a customer's account So that I am able to service the customer's request | * Should be able to view the customer account details before initiating the transaction (US010) * Should display the latest account details after the transaction is completed * Should display user friendly 'Success' or 'Error' response Note : Ref Fig11 – Screens_RetailBank_Casestudy.doc | 10 | 2 | 1 | Deposit money in the account is one of the basic utilities that a banking software should provide.
| US012 | As a Cashier/ Teller I want to be able to withdraw money from a customer's account So that I am able to service the customer's request | * Should be able to view the customer account details before initiating the transaction (US010) * Should display the latest account details after the transaction is completed * Should display user friendly 'Success' or 'Error' response Note : Ref Fig12 – Screens_RetailBank_Casestudy.doc | 10 | 2 | 1 | Withdraw from the account is also a basic service. But it should carefully handeled so there is no deadlock of money.
| US013 | As a Cashier/ Teller I want to be able to transfer money from a customer's account So that I am able to service the customer's request | * Should be able to view the customer account details before initiating the transaction (US010) * Should display the latest account details after the transaction is completed * Should display user friendly 'Success' or 'Error' response Note : Ref Fig13 – Screens_RetailBank_Casestudy.doc | 12 | 2 | 1 | Transfering money is the hard and long part in the developing. Because it needs two account information to be updated.
| US014 | As a Cashier/ Teller I want to be able to print an account statement So that I am able to service the customer's request | * Should be able to choose the no of transactions to be displayed or Start date and End date * Should be able to view the statement online and to be able to get a physical copy * Should display user friendly 'Success' or 'Error' response Note : Ref Fig14.1, Fig14.2 – Screens_RetailBank_Casestudy.doc | 15 | 3 | 1 | Statements of the account will have the least priority because transaction and CRUD operations have to be done before statement creation.