## Sprint 1
Sprint 1 Retrospective
The Good | Continue Doing
Moduler Approach
Focus on small functionality
Reusable code
The Bad | Start Doing - Improvement items/ Agreements on new way of working
Improve URL naming convention
Do proper comments in souce code
Do proper alignment in souce code
The Ugly | Stop Doing
Stop giving ambiguous file name
Stop adding all the design files in the same folder