## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | Login Page Functionality and handeling invalid credentials exception. | Task 1 | Krinal | Design UI of Login Page | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Kamlesh | Design & Create the Database fields for Login | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Kamlesh | Write a program to authenticate user and handling the errors | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Kamlesh | Session Management | 5 | 5 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Kamlesh | Test the home page | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
US002 | Customer database creation. And handelling the Create Customer request. | Task 1 | Krinal | Design UI of Customer page | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Krinal | Design & Create the Database fields for Customer | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Krinal | Write a program to add customer details into DB | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Krinal | Show error message if customer already registered | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Aditi | Test the Customer page | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
Task 6
US003 | Updating the database and handeling the update Customer request. | Task 1 | Krinal | Design UI of Update Customer page | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Krinal | Write a program to update customer details into DB | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Kamlesh | Show error if no customer info is changed | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Aditi | Test the Update Customer page | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Closed
Task 5
Task 6
US004 | Handeling the customer does not exist like queries. And deleting the customer records from the database and also deleting all the accounts of deleted customer. | Task 1 | Krinal | Design UI of Delete Customer page | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Krinal | Write a program to delete customer details into DB | 3 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Krinal | Show error message if customer does not exists or already inactive | 1 | 2 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 4 | Aditi | Test the Delete Customer page | 2 | 1 | 1 | 1 | 0 | 0 | 0 | Closed
Task 5
Task 6
US005 | Designing the status page which countinously shows the latest status of the customer data by page with specific page size. | Task 1 | Krinal | Design UI of Customer Status page | 3 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | Krinal | Write a program to show status of every customer by page number | 4 | 4 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Kamlesh | Write a AJAX program to refresh data | 4 | 4 | 4 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Aditi | Test the Customer Status page | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Closed
Task 5
Task 6
US006 | Creating the Account database and Managing the Create request. | Task 1 | Kamlesh | Design UI of Create Account page | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Kamlesh | Design & Create the Database fields for Account | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Kamlesh | Write a program to add account details into DB | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Kamlesh | Show error message if customer does not exists | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Aditi | Test the Account page | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
Task 6
US007 | Deactivating the account status for the Acconts that are deleted. | Task 1 | Kamlesh | Design UI of Delete Account page | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | Kamlesh | Write a program to delete account details into DB | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 3 | Kamlesh | Show error message if account does not exists or alreay inactive | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 4 | Aditi | Test the Delete Account page | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Closed
Task 5
Task 6
US008 | Continously updating the Account status information to show the latest data page by page with specific page size. | Task 1 | Kamlesh | Design UI of Account Status page | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 2 | Kamlesh | Write a program to show status of every account | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 3 | Kamlesh | Write a AJAX program to refresh data | 6 | 6 | 6 | 6 | 6 | 4 | 0 | Closed
|  | Task 4 | Aditi | Test the Account Status page | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
Task 5
Task 6
US009 | Executing the Search operation on Customer Record by customer ssn or customer id. | Task 1 | Krinal | Design UI of Customer Search page | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Krinal | Write a program to search customer | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Krinal | Show error message if customer does not exists | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Aditi | Test the Customer Search page | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
Task 5
Task 6
US010 | Executing the Search operation for the Account records by account Id or customer id. | Task 1 | Krinal | Design UI of Account Search page | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | Krinal | Write a program to search account | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 3 | Krinal | Show error message if account does not exists | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 4 | Aditi | Test the Account Search page | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Closed
Task 5
Task 6
US011 | Creating the transaction for the amount of deposit and updating the balance of the particular Account. | Task 1 | Krinal | Design UI of Deposit Money page | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 2 | Kamlesh | Design & Create the Database fields for Transaction | 2 | 2 | 2 | 2 | 1 | 0 | 0 | Closed
|  | Task 3 | Krinal | Write a program to deposit money into balance | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 4 | Aditi | Test the Deposite Money page | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Closed
Task 5
Task 6
US012 | Creating the transaction and updating the balance according to the withdrawn money and handle errors of withdraw amount more than balance. | Task 1 | Krinal | Design UI of Withdraw Money page | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
|  | Task 2 | Krinal | Write a program to deposit money into balance | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
|  | Task 3 | Krinal | Show error message if balance is insufficient | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
|  | Task 4 | Aditi | Test the Deposite Money page | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
Task 5
Task 6
US013 | Transfering the money from one account to the other type of the account or to the other customer's account. Inserting the transation of the two Accounts' records. | Task 1 | Aditi | Design UI of Transfer Money page | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Aditi | Write a program to transfer money | 3 | 3 | 3 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Aditi | Show error message if balance is insufficient | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Krinal | Return money into source account if error occurs. | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 5 | Aditi | Test the Transfer Money page | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Closed
Task 6
US014 | Fetch transactions for particular account by start and end date or last number of transactions and also give option for downloading the excel file for the same. | Task 1 | Aditi | Design UI of View/Print Statement page | 1 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Aditi | Write a program to View statement by no. of transaction by page number | 3 | 5 | 5 | 5 | 0 | 0 | 0 | Closed
|  | Task 3 | Aditi | Write a program to View statement by start & end date by page number | 4 | 5 | 5 | 5 | 5 | 0 | 0 | Closed
|  | Task 4 | Aditi | Write a program to download excel of statement | 5 | 5 | 5 | 5 | 5 | 3 | 0 | Closed
|  | Task 5 | Aditi | Test the View/Print Statement page | 6 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
Task 6
|  |  |  | Total | 130 | 111 | 90 | 66 | 45 | 16 | 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
130 | 111 | 90 | 66 | 45 | 16 | 0
144 | 120 | 96 | 72 | 48 | 24 | 0
3 Members
6 Days
8 Hours a day
Total no. of hours =3*6*8=144